## Risk register
BLEEP-SDLC-011 · Risk register
Living register. Likelihood and impact 1–5. Score = L×I. Update when TM-001 bumps.
Risk ID | Risk | TM | L (1-5) | I (1-5) | Score | Stance | Treatment | Owner | Status
R01 | Relay logs rebuild social graph | T7 | 3 | 5 | 15 | Close | No recipient×sender persist; abuse test TV-AB-T7 | Relay eng | Open
R02 | Push body names a person | T10 | 3 | 4 | 12 | Close | Empty FCM template; proxy test | Client | Open
R03 | Malicious lookalike APK | T6 | 4 | 5 | 20 | Mitigate | Publisher ID, hashes, later reproducible builds | Client | Open
R04 | US vendor path for bodies | T19 T23 | 2 | 5 | 10 | Close | No cloud model; no US-only body pipe | Security | Open
R05 | Unlocked stolen phone | T14 | 4 | 5 | 20 | Accept | Lock, disappearing, Chamber burn; honest copy | Product | Accepted
R06 | Peer screenshot / forward | T16 T17 | 5 | 3 | 15 | Accept | Honest UI; no DRM claims | Product | Accepted
R07 | PIN coercion / fake vault demand | T15 | 3 | 4 | 12 | Accept | No decoy Chamber in v1 | Product | Accepted
R08 | Device malware | A7 | 3 | 5 | 15 | Accept | OS hygiene warning only | Security | Accepted
R09 | Export emailed plaintext | T18 | 3 | 4 | 12 | Close | Forced passphrase | Client | Open
R10 | Group fan-out metadata | T7 residual | 4 | 3 | 12 | Mitigate | Small groups only; document residual | Protocol | Open
R11 | Traffic analysis | A10 A2 | 4 | 3 | 12 | Accept | No onion in v1; do not claim otherwise | Security | Accepted
R12 | Chamber treated as PWA | T6 | 2 | 5 | 10 | Close | FC-001 NEVER; architecture review | Product | Open
R13 | Guardian phone-home for safety | T1 T23 | 2 | 5 | 10 | Close | Radio-off test; no model API | Security | Open
R14 | Silent region roam | T21 | 2 | 4 | 8 | Close | Fail closed; chip visible | Relay | Open
R15 | Name-collision apps in stores | TM §10 | 3 | 4 | 12 | Mitigate | Exact publisher + safety-number culture | Product | Open
R16 | ZA demand for metadata | T20 | 3 | 3 | 9 | Mitigate | Minimise; LE guide; Information Officer | Counsel | Open
R17 | Support tool grows a decrypt | STRIDE EoP | 2 | 5 | 10 | Close | No key exists; change control SDLC-009 | Ops | Open
R18 | Mid-range perf / data cost kills retention | Goal 5.2 | 3 | 4 | 12 | Mitigate | Low Data; voice-note first; Loop 1 freeze | Client | Open
Risk count | 18
Average score | 12.5556
Max score | 20
Open or mitigate count | 13

## Heat
Score distribution
Band | Count
Low (1-8) | 1
Medium (9-15) | 15
High (16-25) | 2