## Phase plan
BLEEP-SDLC-012 · Phase and loop plan
Planning sheet. Effort points are relative. Remaining = Planned − Done.
Workstream | Loop | Planned pts | Done pts | Remaining | % done | Exit test | Depends on | Notes
Identity + QR add + local store | 1 | 8 | 0 | 8 | 0% | TV-L1-01 | — | No phone number
Ratchet + sealed mailbox protocol | 1 | 13 | 0 | 13 | 0% | TV-L1-02 | Identity | Library to be bound
Composer text/photo/voice + queue | 1 | 8 | 0 | 8 | 0% | TV-L1-01 | Ratchet | Low Data later
Guardian deterministic rules | 1 | 5 | 0 | 5 | 0% | TV-L1-03 | Composer | Checksums + EXIF + MIME
Lock + empty push + region chip | 1 | 5 | 0 | 5 | 0% | TV-L1-05 TV-L1-06 TV-L1-07 | Mailbox | FCM template review
Signed APK + hash page | 1 | 3 | 0 | 3 | 0% | Release checklist | Client skeleton | Play can trail
Small groups + Status | 2 | 8 | 0 | 8 | 0% | TV-L2-01 TV-L2-02 | Loop 1 | Cap small
1:1 calls + in-region TURN | 2 | 8 | 0 | 8 | 0% | TV-L2-03 | Loop 1 | No recording plane
Chamber vault + pair + burn | 2 | 13 | 0 | 13 | 0% | TV-L2-04 | Loop 1 + lock | Same APK
Inbound Guardian + classifiers pack | 2 | 5 | 0 | 5 | 0% | TV-L2-05 | Guardian L1 | Classifiers CONSTRAINED
Export / unlink / restore | 3 | 8 | 0 | 8 | 0% | TV-AB-T18 | Loop 1 store | Chambers opt-in
Closed ZA ring + LE guide live | 3 | 3 | 0 | 3 | 0% | Compulsion drill | Ops doc | No “secure” word
Bleep box UX | 4 | 13 | 0 | 13 | 0% | New TM pass | Loop 2 | LATER
Desktop native (not PWA) | 4 | 13 | 0 | 13 | 0% | New TM pass | Loop 3 | LATER
Paid protocol review | 3 | 5 | 0 | 5 | 0% | TM §12 gate | Loop 1 protocol bind | Before store “secure”
Total planned | 118
Total done | 0
Total remaining | 118
Overall % done | 0%
Loop 1 remaining | 42
Loop 2 remaining | 34
Loop 3 remaining | 16
Loop 4 remaining | 26

## By loop
Remaining points by loop
Loop | Remaining
1 | 42
2 | 34
3 | 16
4 | 26